Content-Based Epidemic Intelligence for Recurring Seasonal Epidemics

FSE 570 Capstone Proposal

1. Problem Statement

Official disease surveillance systems register an outbreak only after cases have been formally confirmed and reported, which delays recognition of an emerging or intensifying outbreak. Existing informal-source surveillance that relies on report frequency is also unreliable: Ganser et al. (2022) found that HealthMap/EIOS detected only 22 of 238 seasonal influenza outbreaks within a two-week window against WHO FluNet, across 24 countries over seven years of monitoring.

This project asks a plain question: does extracting what informal reports actually say — case counts, severity, symptoms — detect known seasonal epidemics earlier than simply counting how often they are mentioned?

Public health agencies and surveillance teams are the stakeholders: a validated content-based signal gives them an earlier, complementary indicator for recurring seasonal epidemics (influenza, dengue) — an early-warning supplement to official surveillance, not a replacement for it.

Recurring seasonal epidemics impose a substantial, ongoing public health and economic burden every year; even a modest gain in detection lead time supports earlier resource allocation and response.

2. Data Sources

The project uses two genuinely heterogeneous data types: structured numeric surveillance and unstructured multilingual text.

Structured/numeric — influenza: WHO FluNet (xmart-api-public.who.int) — primary structured reference, influenza, country-week, near-global coverage, includes strain subtype breakdown. Confirmed live, no-auth, server-side filterable.

Structured/numeric — influenza (UK gap-fill): UKHSA open dashboard (England weekly test-positivity) — fills a confirmed gap where the UK reports no WHO FluNet data at all; same percent-positivity metric FluNet uses. Confirmed live, no-auth, 8/10 years with a defined onset.

Structured/numeric — dengue (secondary): PAHO PLISA (via Delphi Epidata) and Brazil's InfoDengue (info.dengue.mat.br) — secondary validation reference, dengue, country- and municipality-week respectively. Confirmed live, no-auth.

Unstructured/text — informal reports: GDELT GKG 2.0 / DOC 2.0 API — primary unstructured input, global multilingual news, 2015–present. Confirmed live via the free DOC API and the raw 15-minute GKG file mirror; BigQuery is not required at this scale.

All four sources were tested end-to-end before this proposal was drafted, not assumed — a real strength of the current plan.

Preprocessing challenges already identified through testing: (1) GDELT content depth varies sharply by country — 88% of sampled flu articles were retrievable and content-rich across eight stratified countries in aggregate, but Brazil and Indonesia specifically were confirmed thin-to-absent (33%) across an extended five-day sample, consistent with known income/media-density coverage bias; (2) GDELT's structured geotagging resolves Brazil dengue mentions almost exclusively at country level (0 of 28 checked location entries were subnational), which caps mapping resolution below what InfoDengue's municipality-level ground truth offers; (3) onset-detection thresholds require per-disease, per-region calibration rather than one flat rule.

3. Methodology

The pipeline combines four specific techniques:

LLM-based few-shot event extraction from GDELT-indexed articles into a structured JSON schema — disease signal, severity, symptoms, strain/serotype, location, and confidence — informed by extraction patterns from Health Sentinel and Pant et al. (2025).

Rule-based relevance classification to filter extracted events before aggregation.

Deterministic cross-document linking by (country/city × disease × epi-week) to aggregate multiple reports into a single per-cell signal.

A content-based detection signal evaluated directly against a frequency-count baseline (mirroring Ganser et al.'s original method) — this comparison against the baseline is the project's validation method, not an incidental check.

Evaluation design: a pre-defined cohort with onset dates set independently of any content analysis — 63 flu country-season units across eight stratified countries (income tier × hemisphere), from FluNet directly (UKHSA for the UK cell); plus a secondary dengue cohort of city-season units from Brazilian state capitals, from InfoDengue directly. Onset dates are fixed and held out before any extraction runs. The evaluation metric is detection lead time — the system's first meaningful signal minus the reference onset date — computed for both the content-based method and the frequency baseline on the same cohort.

Validation: the cohort is stratified by income tier, hemisphere, and media density into a calibration subset, used to tune extraction prompts and onset thresholds, and a held-out subset, used only for the final lead-time comparison. No tuning is performed on data used to report results.

4. Project Management

Timeline (through early December):

Sept 15–21: finalize ground-truth cohort and onset dates (flu primary, dengue secondary).

Sept 22–Oct 5: GDELT ingestion at scale for cohort countries and cities.

Oct 6–19: build the extraction pipeline (LLM few-shot schema extraction).

Oct 20–Nov 2: relevance classification and cross-document linking.

Nov 3–16: lead-time evaluation — content-based signal vs. frequency baseline.

Nov 17–23: country-level relative-intensity mapping.

Nov 24–Dec 5: writeup and final report.

This schedule reflects a scope that is now settled after four disease-domain reframes were resolved through feasibility testing prior to build start.

Status check-ins are aligned with course-specified status check-ins. By each checkpoint, the following should be true in sequence: ground-truth cohort finalized; extraction pipeline producing structured output on a validation sample; baseline and content-based lead times both computed.

Top risks:

Uneven cross-country GDELT content coverage (confirmed: Brazil/Indonesia thin vs. USA/UK/Japan/Australia/Kenya/India strong) — monitored via per-country retrievability/content-depth rate; mitigated by prioritizing cohort countries with confirmed adequate coverage and disclosing thin-coverage countries as a limitation rather than assuming uniform coverage.

LLM extraction accuracy ceiling (comparable published systems report roughly 60–90% depending on task) — monitored via a held-out labeled validation sample; mitigated by iterative few-shot prompt refinement, treating extraction accuracy as a reported metric rather than an assumption.

Onset-threshold sensitivity for the seasonal cohort — already identified and mitigated during feasibility testing: a flat incidence/positivity threshold misreads baseline-variable regions (a 25x spread in dengue city baselines), so the build uses city- and country-relative thresholds instead of one flat rate.